Vasundhara Infra Ltd (DEMO)

Ref: VIL/HPA/2026/112

Date: 09/09/2026

To: The Project Director, Highway Package A PIU (DEMO)

From: Vasundhara Infra Ltd (Contractor, DEMO)

Subject: Notice of delay - Pier P17 concreting - cement supply

Dear Sir,

This is to notify you that the concreting of Pier P17 could not proceed on 08/09/2026 owing to non-availability of cement at site. The supplier has confirmed dispatch.

We expect to resume concreting on 12/09/2026 and to complete Pier P17 by 14/09/2026.

This letter is notice of a delay event under Clause 19.1 of the Contract.

Yours faithfully,

Project Manager, Vasundhara Infra Ltd (DEMO)