## Tasks
JARVIS Project — Task Tracker
ID | Task | Owner | Priority | Status | Due Date | Notes
1 | Fix UI QLabel / cursor bugs | Dev | High | Done | 2026-08-26 | hud_window
2 | Multi-model router | Dev | High | Done | 2026-08-25 | models/router
3 | OCR install (Tesseract) | Ops | High | In Progress | 2026-09-10 | PATH required
4 | RAG + BGE reranker | Dev | Medium | In Progress | 2026-09-15 | ollama pull
5 | PPT intelligence engine | Dev | Medium | Planned | 2026-09-20 | python-pptx
6 | Excel KPI templates | Dev | Medium | Planned | 2026-09-20 | openpyxl
7 | Industrial knowledge ingest | Data | High | Planned | 2026-09-18 | scripts
8 | Voice model setup | Ops | Medium | Blocked | 2026-09-12 | setup_models.py
9 | Security login / vault | Sec | High | In Progress | 2026-09-22 | argon2
10 | Demo dry-run | Team | High | Planned | 2026-09-25 | 10 min script
Open tasks count: